## Group Contribution Log
Course | CS3343
Term | 2025-26 Semester A
Project No. | 5
Project Name/Title | Sport Facility and Equipment Booking System
No. of Team Members | 6
Project Manager Name | NG KA HUNG
Student ID | Name (Last, First) | Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Week 6 | Week 7 | Week 8 | Week 9 | Week 10 | Week 11 | Week 12 | Week 13 | Total | Student | Relative | Contribution | e.g.Group Mark | Final Adjusted
58537137 | Lau Wing Him | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 13 | Lau Wing Him | 1 | 100% | 80 | 80
58120400 | Ip Wing Kai | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 13 | Ip Wing Kai | 1 | 100% | 80 | 80
58533974 | Chan Sing To | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 13 | Chan Sing To | 1 | 100% | 80 | 80
58537684 | Lin Weiyuan | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 13 | Lin Weiyuan | 1 | 100% | 80 | 80
57925345 | Lee Kin Wai | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 13 | Lee Kin Wai | 1 | 100% | 80 | 80
58533046 | Ng Ka Hung | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 13 | Ng Ka Hung | 1 | 100% | 80 | 80
| Total Effort | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 78 | Max | 1 |  | Average | 80
[19 empty] | Max | 80
[19 empty] | Min | 80

## Weekly Activity Log
Week | Weekly Activity Log | Completed By
Week 1 | Recruit Project Memebers to Form a Team. | NG KA HUNG
Week 2 | Decide Project, brainstorming project ideas and study | All Team
Week 3 | Requirement gathering, set up requirement for criteria of how project could be successful | All Team
Week 4 | Project plan, create Work Breakdown Structure, Design Analysis & Design (system analysis, use case) | All Team
Week 5 | Design Analysis & Design (class diagram), Set up software environment, Software development (equipment, facility, book record item) | All Team
Week 6 | Software development (Book Facility, Book Equipment, Sell Equipment) | All Team
Week 7 | Software development (Book Facility, Book Equipment, Sell Equipment, View Current Booking) | All Team
Week 8 | Software development (Book Facility, Book Equipment, Sell Equipment, View Current Booking, View Confirmed Booking) | All Team
Week 9 | Software development (View Confirmed Booking, UI), Testing, Debug | All Team
Week 10 | Testing, Debug, Documentation | All Team
Week 11 | Testing, Debug, Writing reports | All Team
Week 12 | Writing reports | All Team
Week 13 | Writing reports, Presentation | All Team